## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
User App Andriod
| Table 1 | User App Andriod
User App IOS
| Table 1 | User App IOS
Staff App IOS
| Table 1 | Staff App IOS
Staff App Android
| Table 1 | Staff App Android
Student Web Portal
| Table 1 | Student Web Portal
Teacher Panel
| Table 1 | Teacher Panel
Improvements for user app
| Table 1 | Improvements for user app
Improvements for staff app
| Table 1 | Improvements for staff app

## User App Andriod
S. No. | Date | Ponits | Remarks By us Team | Remarks of Lalit khurana whereever require | Remarks By Isoftnic
2 | 18th April 2024 | Course banner’s are not displaying. , change client testimonial to user review and how they will review? | Pending | As discussed with Mr Vijay , he will give some place where admin can put review and comments from side for courses | Done
3 | 18th April 2024 | Change go to home to Go To My Booking | done by lalit | please refer below snapshot for improvement, it is not error
4 | 18th April 2024 | In left menu Support button Add valiation on mobile Number & Email id | Pending | please refer below snapshot, form is accepting wrong information and not auto populate from user profile and do not warn to user for wrong email id , This form should automatically pick up name, mobile number and email id from user profile. | Done
5 | 18th April 2024 | Analytics report button is not available | it was moved under course section - lalit |  | Done @Vijay sir
6 | 18th April 2024 | in which series we are putting information in admin portal , in same series videos are not appearing in Application, please refer below snaopshot from admin portal and application | done - lalit | This is Error and we have to fix it, videos should be in same sequense we are putting in admin portal.
7 | 18th April 2024 | Information putting in admin portal is not correctly appearing in application , in previous versions, information is correctly working appearing now it is not not correctly appearing. | done - lalit | This is Error and we have to fix it. Information is not correctly appearing in application from admin portal.
8 | 18th April 2024 | Business Document page has been removed from Left hand side menu | Pending at lalit part | Please fix this error
9 |  | MCQ - It shows error - it do not MCQ and shoes message - Test not available yet | done - lalit | Please fix this error , We have already uploaded MCQ on server using admin portal but it did not show in app
10 |  | Subtitle - option is not appearing on video section - Subtitle is already uploaded on server while it did not show in application. | CLOSED BY LALIT | Please fix this error
11 |  | Notes - We have uploaded notes on server while nothing is shown in application and it appear message " No Preview available | CLOSED BY LALIT | Please fix this error
12 |  | while purchase course , it automatically shows course is 100% complete |  | Please fix this error | Done
13 |  | Social Media section - Application is not working when we click on categories |  | Please fix this error | Done
14 |  | Search button is not working and how it will work ?? ( please refer below snapshot) |  | Please fix this error | Done
Course section
15 | 2024-05-07 | Vidoes will be running in sequence manner, presently user can see any video in any manner ( please refer below snapshot)
16 | 2024-05-07 | After 100 percent completion of course , Student can download its certificate, previously this section was there in app , now i cant see any option to download certificate from app after completion of course. ( please refer below snapshot) |  |  | Upload certificate course wise pending
17 |  | Video title name missing (Please refer below snapshot) |  |  | Done
18 |  | in doubt section, course name Add course & add in teacher panel also (Please refer below snapshot) |  |  | Done
19 |  | After submitting the contact us form user can't see admin reply on app. |  |  | Done
20 |  | social section when we added a new post then profile image is not coming & shiivam static name is also coming |  |  | Done
| Point no 3 | After course purchase , below page appear,
Instead of link "Go to Home" There should be link to "go to Course"
becuase all users want to see its puchased course after making payment instead of going to home page
| Point number 4 | Form is accepting wrong email ids,
| Point no 5 | Analytics report button is not avaiable
| point no 6 | in which series we are putting information in admin portal , in same series videos are not appearing in Application, please refer below snaopshot from admin portal and application
| 6A | in admin portal, introduction of accounting is on top and in application it goes at the bottom
| 6B | in similar way , Vidoes putting in that chapter is also shuffle and did not appear in same sequence number in which we have uplloaded on admin portal.
| Admin Portal |  |  | Application
| Point number 7 | Information putting in admin portal is not correctly appearing in application
in previous versions, information is correctly working appearing now it is not not correctly appearing.
| Admin portal |  |  | Application | Previous version
| Point no 8 | Business Document page has been removed from Left hand side menu
in previous version, business document was in left menu, and appear in below manner
Now this page has been removed from application from left menu
Point no 9
Point no 10
Point no 11
Point no 12
| Point no 13 | These buttons are not working
| Point no 14 | Search button is not working and how it will work ??
| Point no 15 | Vidoes will be running in sequence manner, presently user can see any video in any manner
| Point no 16 | After 100 percent completion of course , Student can download its certificate, previously this section was there in app , now i cant see any option to download certificate from app after completion of course.
| Point no 17 | Video title name missing
| Point no 18 | Please show course name in this snapshot
(Please refer below snapshot)

## User App IOS
S. No. | Date | Ponits | Remarks By us Team | Remarks of Lalit khurana whereever require | Remarks By Isoftnic
1 | 5th may 2024 | While entering password it’s not showing alphabets, only numbers are showing | done
2 | 5th may 2024 | It’s not showing login with “gmail account” option. | done
3 | 5th may 2024 | Icons are not showing | done
4 | 5th may 2024 | Can’t able to post video and images, it’s not clickable | pending
5 | 5th may 2024 | Coupons are not applying from “offer section” | done
6 | 5th may 2024 | Reel and post “like and dislike” option is not highlighting | done
7 | 5th may 2024 | Subtitle option is not showing in videos | pending
8 | 5th may 2024 | Offers section is missing in left side menu. | done
9 | 5th may 2024 | Share button is not working in left side menu | done
11 | 5th may 2024 | These are old graphics, use the same graphics as of android user app. Also write “next” on the marked area. | done
12 | 5th may 2024 | If we log on different devices with same account, it should automatically be logout from another device. | done
13 | 5th may 2024 | While login in ios it’s sending 2 otp’s. | done
14 | 5th may 2024 | don't able to share reel | pending
15 | 5th may 2024 | not able to see some videos after purchasing course | pending
16 | 5th may 2024 | name of reel poster is not visible in reel section | pending
17 | 5th may 2024 | in social option like post is not working and comment is not showing from outside | pending
18 | 5th may 2024 | my doubt is not working | pending
19 | 5th may 2024 | please tell how webinar section work | pending
Point No 4
point 14
Point No. 7
point 15
point 16
point 17

## Staff App IOS
S. No. | Date | Ponits | Remarks By us | Remarks By Isoftnic
1 | 2024-04-18 | Change app Icon | Pending
2 | 2024-04-18 | there's a glitch in my profile section, see screenshot, | Pending
3 | 2024-04-18 | Create New Leads is missing in utilities | Pending
4 | 2024-04-18 | While creating new lead filling lead's infomation in form all details of lead it's filled up all the same as the name automatically | Pending
5 | 2024-04-18 | Notifications is not working in IOS | Pending
6 | 2024-04-18 | My Office is completely different from Andriod | done
7 | 2024-04-18 | Social Media is completely not working | Pending
8 | 2024-04-18 | Creative are empty and no button is working | Pending
9 | 2024-04-18 | Not able to download Certificate in my Activity + Change correct spelling of Download (Dowload To Download) | Pending
10 | 2024-04-18 | Share to lead & Share on social button is not working in Digi-Bazzar | Pending
11 | 2024-04-18 | Share to lead & Share on social button is not working in Creative | Pending
12 | 2024-04-18 | Share button in Refer earn is not working | Pending
13 | 2024-04-18 | Not able to post in social media | Pending
14 | 2024-04-18 | Not able to download in Business document + Change correct spelling of Download (Dowload To Download) | Pending
15 | 2024-04-18 | About Us is missing | Pending
16 | 2024-04-18 | Privacy & Policy (create inbuilt privacy & policy) Remove downloadable type of documents in privacy & policy | Pending
17 |  | In my office section, task to do is incomplete as compared to Mockup
Point No. 1
Point No. 2
Point No. 4
Poin No. 6
Point No. 7
Point No. 9
Point No. 10
Point No. 14
Point No. 16
| Point number 17 | In my office section, task to do is incomplete as compared to Mockup

## Staff App Android
S. No. | Date | Ponits | Remarks By us | Review points by Mr Khurana | Remarks By Isoftnic
1 |  | As discussed with previously, create short of "Create Lead"at Left Menu |  | yes i have already discussed this in last meetings
2 | 2024-04-18 | Screenshot-2 is missing in staff app. | Pending | It appear, Programmer missed to see second page of form in ock up and he has created form having content of page number 1, please advise team to see second page of form in Mock up and fix this issue.
3 | 2024-04-18 | Send payment link and delete button is missing Screenshot-3 | Pending | Pleae advise Programmer to fix this issue
4 | 2024-04-18 | Screenshot-4 from where we can change the banner ?? There is no option available on Admin Portal to change banner of this page | Pending | ok
5 | 2024-04-18 | Change “digital dukaan” to “Digi-Bazzar” and while sharing creatives on social media it should look like the shared image. (see screenshot number -5) | Pending | i have solution for it, i will call to Mr Vijay and discuss. We have to fix it Can we fix some portion of Frame i which QR code to download application and company name will be fixed and while sending message/share on social media, message will take information from Profile (Vijay ji adivse it to me over phone)
6 | 2024-04-18 | We can’t see other users post on social post and post are not displaying category wise in social media. (we can see all users post whether we followed them or not) {App stop working while clicking on the social post button} So it’s still pending. | Pending | it is bug please fix it
7 | 2024-04-18 | How Notifications works in left menu? Notifications are not appearing while sendig notification from Admin portal. | Pending | it is bug please fix it
8 | 2024-04-18 | In “support” section, error should be shown to us if wrong information and number is filled. (see screenshot number -6) | Pending
9 | 2024-04-18 | training video, Gen leads & leads call are missing in Task earning. Programmer missed to create few tabs in this form such as Training videos, Gen Leads and Lead calls (please refer below snapshots) | Pending | Please advise programmer to fix it
10 | 2024-04-18 | Bio, View Fee Status & course are missing in my profile and Design of my profile is way different from mockup. Course button is missing in this page, view fee status course etc is missing | Pending
11 | 2024-04-18 | Please inform us from where contact information will update/change. Please advise option to update Channel Partnes, Regional Manager and Zonal manager etc details at this page | Pending | i think it is under development , please advise vijay ji
12 | 2024-04-18 | Search option is not working properly in my network, all contacts should be there, provide alphabetical filter for all contacts in the right side of the screen and also inform us from where we can change banner of my network. | Pending | Please refer below to see out comments in detail.
13 | 2024-04-18 | In business documents please create a folder tree in it. | Pending | Please refer improvement page for it
14 | 2024-04-18 | Download certificate button is missing and buy course button is also missing in course & {App stop working while clicking on the Course button} So it’s still pending. Please refer below to see out comments in detail. | Pending | Programmer to missed to create it
16 | 2024-04-18 | Videos are not according to serial wise and Design of videos is way different from mock up. See in detail. | Pending
17 | 2024-04-18 | We have uploaded a test MCQ but it’s not showing in app. This option is not properly working | Pending | This option is not properly working
18 | 2024-04-18 | We have tested notification it’s not working and there no history for notifications to check whether it’s seen or not in admin portal. Please refer below to see out comments in detail. | Pending | yes history of notifiction must be there for internal control purpose
19 | 2024-04-18 | Send button is not working in Contact us in app , that means we are not getting these messages to reply to our staff. Also advise from where we can access these messages to reply ?? | Pending | please refer below snapshot, form is accepting wrong information and not auto populate from user profile and do not warn to user for wrong email id , This form should automatically pick up name, mobile number and email id from user profile. i think we are also creating ticket system to control it, vijay ji please advise on it ??????
20 | 2024-04-18 | Policies is still not updated in app. Please refer below for our detailed comments for this point | Pending | There should be in application only
| Point no 1 | As discussed with previously, create short of "Create Lead"at Left Menu
| Point No. 2 | Few tabs are missing in create lead such as, there are 2 pages of form in Mock up while programmer has worked in first page and forget to work in 2nd page
1. Select product type, User level, Payment status, Amount , etc... all details which are mentioned in below snapshot
| present Form in Application | Form in Mock up
| Point No. 3 | Please refer belowsnapshots, Send Payment link and delete lead is missing in present application
Pleae advise Programmer to fix this issue
| Present form in application | Form in mockup
| Point No. 4 | There is no option available on Admin Portal to change banner of this page
| Point No. 5 | This is different from Mock up page
Can we fix it in that manner so that QR code of application will go with creatives, so that peolple can download out application from any creative.
| Point No. 8 | If anyone out wring name, email id or any detail then form is accepting wrong inputs as well
This form should automatically pick up information from profile.
| Point No. 9 | Please refer snapshot from Mockup
Programmer missed to create few tabs in this form such as Training videos, Gen Leads and Lead calls
Please advise programmer to fix it
| Present form in application | Form in mockup
| Point No. 10 | Course button is missing in this page, view fee status course etc is missing
| Present form in application | Form in mockup
| Point No. 11 | Please advise option to update Channel Partnes, Regional Manager and Zonal manager etc details at this page
| Present form in application | Form in mockup
| Point No. 12 | Point to be fixed :-
| 1 | Search option in this page is not working
| 2 | There must be option at the right hand side to sort contacts "Älphabet wise"
| 3 | All Contact are not loaded one time, we have drag down again and again to refresh page then it will show some more contacts and app is taking more time than usual to show more contacts.
| Point No. 13 | Please see improvement page to fix this
we need right to create folders to manage documents
This page is free for all to download documents , User can download these documents in their mobile
| Present form in application | Form in mockup
| Point No. 15 | Point to fix in this page
Downlaod Certificate button is missing
% perentage completion is not proper it should be 25% then 50% then 75%
| Present form in application | Form in mockup
Point No. 18
| 1 | Sending notification is not proerly working
| 2 | we have tried to send notification but this system is not working properly
| 3 | Histrory of sending notification is not found, we must have history to check whether correct notifcations are sending to students / Staff
| 4 | Point no 3 is must for internal control purpose
| Point No. 19 | please refer below snapshot, form is accepting wrong information and not auto populate from user profile and do not warn to user for wrong email id , This form should automatically pick up name, mobile number and email id from user profile.
| Point No. 20 | There should be in application only
There should be no option to download policies, if anyone want to read then he/ she has to read in app only
There should be confirmation from user/staff to use this application, there should be box in which by ticking he will give his acceptance . such like we will give it to google

## Student Web Portal
S. No. | Date | Ponits | Remarks By us | Review points by Mr Khurana | Remarks By Isoftnic
1 | 2024-05-06 | Immediate after purchase of course , it shows under Completed Course while it should be transfer in completed course only after completing whole course (Please refer below snapshot)
2 | 2024-05-06 | When we click on Exam Start Tab - it shows blank page, please advise how it will work (Please refer below snapshot)
3 | 2024-05-06 | When iwe click on course report, it shows this error. (Please refer below snapshot)
4 | 2024-05-06 | When we client on Business document page, it shows wrong file name, please fix this error so that it shows correct file name. (Please refer below snapshot)
5 | 2024-05-06 | PDF file attached with course video is not opening, it shows error (Please refer below snapshot)
6 | 2024-05-06 | MCQ Section is missing in web portal
7 | 2024-05-06 | Please refer above snapshot and advise purpose of Actions, What is use of this button. (Please refer below snapshot)
8 | 2024-05-06 | Also advise "how live class"seection will work.
Snap Shots
Point no 1
Point no 2
| Point no 3 | When iwe click on course report, it shows this error.
| Point no 4 | When we client on Business document page, it shows wrong file name, please fix this error so that it shows correct file name.
| Point no 5 | PDF file attached with course video is not opening, it shows error
| Point no 6 | MCQ Section is missing in web portal
| Point no 7 | Please refer above snapshot and advise purpose of Actions, What is use of this button

## Teacher Panel
S. No. | Date | Ponits | Remarks By us | Review points by Mr Khurana | Remarks By Isoftnic
1 | 2024-05-06 | Teacher can review only 10 students at a time, there should be option to see upto 100 students in one page ( Please refer below snap shot)
2 | 2024-05-06 | Please refer below snap shot, Subject name is missing in first line. We have checked in Super Admin, name was already there but it is not properly showing here. ( Please refer below snap shot)
3 | 2024-05-06 | When we client on Courses- it shows below error. ( Please refer below snap shot)
4 | 2024-05-06 | When we client on live classes - it shows below error. ( Please refer below snap shot)
5 | 2024-05-06 | When we client on Total Exams and Total Time Table - it shows below error. ( Please refer below snap shot)
6 | 2024-05-06 | Please advise when teacher will reply on doubts then where student can see this reply. ( Please refer below snap shot)
7 | 2024-05-06 | Please advise from where Teacher will upload student wise marks
| Point no 1 | Teacher can review only 10 students at a time, there should be option to see upto 100 students in one page
| Point no 2 | Please refer below snap shot, Subject name is missing in first line. We have checked in Super Admin, name was already there but it is not properly showing here.
| Point no 3 | When we client on Courses- it shows below error.
| Point no 4 | When we client on live classes - it shows below error.
| Point no 5 | When we client on Total Exams and Total Time Table - it shows below error.
| Point no 6 | Please advise when teacher will reply on doubts then where student can see this reply.

## Improvements for user app
Point no 1 | Business Documents
| Present look |  |  | Proposed Changes
|  |  | A | It must have right to create folders -
|  |  | 1 | Topic Wise
|  |  | 2 | Subject wise
|  |  | 3 | Chapter wise
|  |  | 4 | Any more
|  |  | B | We should have create folder as per need
|  |  | C | search option at all lever to find files with name
|  |  | D | We need additional short cut at left hand side Menu for Busines Documents in user app. these are free of cost for all
Do not remove link preiously created under course section
Point number 2
At this page, we need one more folder beside MCQ
In that folder there should be 2 categories , 2 folders
in 1 folder , we can save files (word, Excel, Pdf, PPT, etc..)
In 2nd folder we can upload solutions in video
only pdf, ppt and word files can be opened in app and rest excel file can be downloadable in system
Point no 3
| Need to connect API of job portal |  |  | Already Shared excel sheet for it
Point o 4
Need to connect API for Chatbot for mentorship
Point no 5 | We have taken Easebuzz payment gateway in the month of August 23 and due to non activity from last six months, they have closed our acccount
Now we are taking payment gateway from ICICI Bank which is directly linked with our bank accounts, please change it as per document received from ICICI Bank
Point no 6 | Examination fees
There is no section in application to collect examination fees from students per semister, please discuss for it.
Point no 7 | In front page there is no option for user to contact us, Can we create any tab or short cut which user can contact our customer care
Point no 8 | Security features are missing
| A | only login at 1 app and all other logins will be automatically loged out
| B | if person change phone fequently then system should inform to admin
| C | person mobile number should be highlight on video to control
| D | no snapshot and no recording allowed